| Meeting dates & times /Tasks Comments | Mon 4th Feb 15h00 (BANG) | Mon 11th Feb 12h00 | Mon 18th Feb 10h00 | Mon 25th Feb 12h00 | Mon 3rd March 10h00 | Mon10th March 12h00 | Thurs 20th March 10h00 | Wed 2nd April 12h00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Combined meeting (IM Venter) | Combined meeting (IM Venter & WD Tucker) | Combined meeting (IM Venter & WD Tucker) Identify someone (Writing Centre) to read your doc. | Separate meetings | WD Tucker (IM Venter out of the country) | Separate meetings |  |
| Thesis Document | Create document using Honours Project Guidelines from the website as well as Thesis doc from Word | See previous week! Complete the thesis outline (using Honours Project Guidelines) | See that you understand how to use the Styles and how to compile an Index, the Table of Contents, List of Figures etc. | and start with RAD. | - Check Index and add indexes - Bibliography – at least 5 entries. | Finalise write-up. Let someone proof read your document! | Hand in final document on Friday (20th March) before 12h00. |  |
| URD | Fill in headings | Start write-up of URD. | Continue with URD write-up. Interview stakeholders. Interview with the DCCT{deaf community of cape town}, in particular Gavin. | Complete URD |  |  |  |  |
| RAD | n/a | Fill in headings |  | Start write-up of RAD. | Write-up RAD | Complete RAD |  |  |
| Literature Survey | Familiarising yourself with your topic, and how it's implemented. Read and explore. literature on your topic. | Read and explore. some more – use Google Scholar.. | Add all literature found to your bibliography – use the Harvard Notation | Keep on reading |  |  |  |  |
| Presentation/deliverable | Write one paragraph that describes what you want to do, and why you want to do it |  |  |  |  | Use thesis to Prepare slides for mock presentation | Mock presentation | 2th April Present |
| Website | Ask Verna Connan or Carlyn for access to put up your web-sie | See previous week! Create website | Put plan onto website, upload the website. |  | Ask Carlin about the server. Add URD to website | Add RAD to website |  | Put presentation on website |

RED means completed.

BLACK means still to be done